IAM SYSTEM DEPLOYMENT — PROJECT PLAN v1.0

Sections 7, 9, 12 and 14

Kritika Bhattarai · Resource and Communications Manager

Your sections only, taken from the full plan (plan/IAM_ProjectPlan_v1.0.docx). Table, figure and reference numbers match the full plan, so some numbers are skipped. If you change anything here, send the change to Toufiq so it goes into the full plan before release.

# 7. Resource allocation and responsibility matrix

Section owner: Kritika Bhattarai

Table 10 assigns responsibility for each major deliverable using RACI: Responsible (does the work), Accountable (approves it; exactly one per row), Consulted and Informed. Assignments were levelled so that no named person and no IAM Architect is booked on two work packages at once (apart from the level-of-effort package 1.1.4). This is why privileged access management (1.3.4) and access review campaigns (1.3.5) follow the MFA policies (1.3.3) instead of running alongside them.

Table 10. RACI matrix

| Deliverable (WBS) | Sponsor | PM (Toufiq) | Res. & Comms (Kritika) | QA Lead (Fardin) | Change & Config (Mahir) | IAM Architect | Partner | HR | IT Ops |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project charter and management plan (1.1.1, 1.1.3) | A | R | C | C | C | C |  | I | I |
| Stakeholder register and communication plan (1.1.2) | I | A | R | I | I | I | I | C | C |
| Current-state assessment (1.2.1) | I | A |  | C | C | R |  | C | R |
| Requirements and privacy impact assessment (1.2.2–1.2.3) | I | A | C | R |  | R |  | C | C |
| Platform selection and contract (1.2.4, M3) | A | R | I | R | I | C |  |  | C |
| Role model (1.2.5) | I | A |  | C | I | R | C | R | I |
| Solution architecture and security design (1.2.6) | I | A | I | C | C | R | C | I | C |
| Platform build: JML, MFA, PAM, access reviews (1.3) |  | I | I | C | I | A | R | C | C |
| SSO and provisioning integration (1.4) |  | I | I | C | I | A | R |  | C |
| Testing: system, penetration, user acceptance (1.5) | I | I | C | A | I | C | R |  | C |
| Training and adoption (1.6.1) | I | I | A | C | R | C | C | C | R |
| Pilot, rollout and hypercare (1.6.2–1.6.4) | I | A | C | C | R | C | R | I | R |
| Risk register and issue log | I | A | R | C | C | C | I | I | I |
| Change control and configuration management | C | A | I | C | R | C | C |  | I |
| Quality assurance reviews and audits | I | A | I | R | C | C | C |  | I |
| Handover and closure report (1.7) | A | R | C | C | R | C | I | I | C |

Table 11 estimates labour and other costs. Rates are fully loaded, assume a 38-hour week and exclude GST. The contingency reserve equals the total expected monetary value of the risks in Section 8.

Table 11. Resource and cost estimate (AUD)

| Resource or item | Person or source | Allocation | Hours | Rate/h | Cost |
| --- | --- | --- | --- | --- | --- |
| Project Manager | Toufiq Ahmed Joy | 100% × 39 wks | 1,482 | 115 | 170,430 |
| Resource and Communications Manager | Kritika Bhattarai | 50% × 39 wks | 741 | 90 | 66,690 |
| Quality Assurance Lead | Fardin Rahman Tanvir | 50% × 39 wks | 741 | 90 | 66,690 |
| Change and Configuration Manager | Ahmed Mahir Daiyan | 50% × 39 wks | 741 | 90 | 66,690 |
| IAM Architect (contract) | To be engaged | 80% × 35 wks | 1,064 | 150 | 159,600 |
| HR systems analyst | People and Culture | 20% × 20 wks | 152 | 75 | 11,400 |
| Service desk and IT operations | IT Operations | 50% × 16 wks | 304 | 70 | 21,280 |
| Implementation partner (fixed-price SOW) |  |  |  |  | 185,000 |
| IAM platform subscription, year 1 (1,500 identities) |  |  |  |  | 162,000 |
| FIDO2 security keys for shared workstations and admins (650) |  |  |  |  | 55,250 |
| Independent penetration test |  |  |  |  | 28,000 |
| UAT backfill shifts for clinical testers |  |  |  |  | 32,000 |
| Training delivery and materials |  |  |  |  | 15,000 |
| Work package estimate |  |  |  |  | 1,040,030 |
| Contingency reserve (risk EMV, Section 8) |  |  |  |  | 159,000 |
| Cost baseline |  |  |  |  | 1,199,030 |
| Management reserve (sponsor) |  |  |  |  | 50,970 |
| Budget ceiling |  |  |  |  | 1,250,000 |

# 9. Issue management strategy

Section owner: Kritika Bhattarai

A risk might happen; an issue has happened and needs action now. When a risk occurs, its owner starts the contingency and logs an issue. Table 16 sets out how issues are handled. The log is reviewed weekly, P1 issues are reviewed daily until closed, and open issues go in the monthly sponsor report.

Table 16. Issue handling steps

| Step | What happens | Who |
| --- | --- | --- |
| 1. Log | Record the issue within one working day as a Jira card of type Issue; the issue log (templates/issue_log.csv) mirrors it | Anyone |
| 2. Prioritise | Set priority P1–P4 using Table 17 | Workstream lead |
| 3. Assign | Name a single owner and a target date | Workstream lead |
| 4. Escalate | If not resolved within the response time, escalate as in the priority table. An issue that needs more time, money or scope becomes a change request (Section 10) | Owner |
| 5. Close | Record the action taken and close. If the issue revealed a new risk, add it to the register | Owner; project manager closes |

Table 17. Issue priorities, response times and escalation

| Priority | Definition | Owner assigned | Escalate if unresolved |
| --- | --- | --- | --- |
| P1 Critical | Stops clinical work, go-live or a gate, or is a security incident | Within 2 hours | Project manager immediately; sponsor within 24 hours |
| P2 High | Threatens a critical-path task or milestone date | Within 1 working day | Project manager after 2 days; sponsor or CCB after 5 days |
| P3 Medium | Affects a task that still has float | Within 3 working days | Workstream lead, then project manager after 10 days |
| P4 Low | Minor; no schedule effect | Next weekly meeting | Project manager at the weekly review |

Table 18. Issue log template (the two rows are examples of how to fill it in)

| ID | Raised | Description | By | Priority | Owner | Action | Status | Closed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| I-001 | 12 Jan 2027 | HR export has no end dates for 41 contractor records, so leaver rules cannot run for them | IAM Architect | P2 | Kritika (with HR) | HR backfills end dates; contractor coordinator confirms them | Closed | 20 Jan 2027 |
| I-002 | 2 Mar 2027 | Pathology portal vendor's test environment is unavailable for wave 3 | Partner | P3 | Mahir | Vendor escalation; test against staging copy if not fixed in 5 days | Open |  |

# 12. Communication management plan

Section owner: Kritika Bhattarai

Table 24 lists every stakeholder from the charter, plus the project team and the CCB. For each it shows what they need to know, how and how often they hear it, and who sends it. The tools are:

- Microsoft Teams for meetings: a 15-minute stand-up three times a week and a weekly status meeting;

- Jira for tracking tasks;

- GitHub for documents and baselines;

- email and the intranet for reaching staff.

Problems are escalated as set out in Section 9.

Table 24. Communication plan

| Stakeholder | Information needed | Method | Frequency | Owner |
| --- | --- | --- | --- | --- |
| Project sponsor | Status against baseline; top risks and issues; decisions needed | One-page status report and 30-minute meeting | Fortnightly; at each gate | Toufiq |
| Executive leadership team and Board Audit and Risk Committee | Progress to the Essential Eight target; budget; key risks | Written briefing | Monthly (ELT); quarterly (committee) | Toufiq |
| Head of Information Technology | Design decisions; handover readiness | Steering meeting; design reviews | Fortnightly | Toufiq |
| IT operations and service desk | Build progress; runbooks; rollout dates; known issues | Teams channel; weekly operations sync; knowledge articles | Weekly; daily during rollout | Mahir |
| Clinical staff and the Director of Nursing | What changes, when; how to enrol; where to get help | Champions at site huddles; intranet news; quick-reference cards | Monthly; weekly from 4 weeks before their site goes live | Kritika |
| Administrative and corporate staff | What changes, when; how to enrol | Email; intranet; short videos | Monthly; weekly before rollout | Kritika |
| Contractors, agency staff and visiting medical officers | Enrolment steps; how to request access | Email through agency coordinators; onboarding pack | At onboarding and before rollout | Kritika |
| People and Culture (HR) | Data quality issues; changed joiner-mover-leaver process | Working session | Weekly during design and build; then fortnightly | Kritika |
| Privacy Officer and compliance | Privacy impact assessment; data residency; audit evidence | Meeting and assessment report | During 1.2.3 and at each gate | Fardin |
| IAM platform vendor and implementation partner | Tasks, defects, change requests | Jira board; weekly delivery meeting | Weekly | Toufiq |
| Application owners | Integration dates; test windows; cut-over and rollback plans | Email and integration meeting | 2 weeks before and during their wave | Mahir |
| Project team | Tasks, blockers, decisions | Jira; Teams stand-up; GitHub pull requests | Stand-up 3 times a week; weekly status meeting | Toufiq |
| Change control board | CRs with impact assessments | CR pack and meeting | Fortnightly, or within 2 days if urgent | Mahir |

# 14. Conclusion

Section owner: Kritika Bhattarai

This plan turns CHG's audit findings into a funded, scheduled project.

- Research (Section 2): identity remains a major way into Australian health providers, and only phishing-resistant MFA meets the Essential Eight benchmark. That sets the technical direction.

- Objectives (Section 3): seven measurable targets, from MFA for all 1,500 identities to finishing within budget.

- Charter (Section 4): names the sponsor, fixes 12 applications in scope, lists what is out of scope and sets a budget ceiling of AUD 1,250,000.

- WBS (Section 5): 29 work packages in seven branches, plus seven milestones.

- Schedule (Section 6): 182 working days from 2 Nov 2026 to 28 Jul 2027, with go-live on 16 Jun 2027, before the 30 June target.

- Resources (Section 7): one accountable person per deliverable and a cost baseline of AUD 1,199,030.

- Risk (Section 8): 12 risks, 5 of them High, each with a mitigation, a contingency and a trigger. Their combined EMV funds the AUD 159,000 contingency reserve.

- Issues (Section 9): four priority levels, each with a set escalation path.

- Change control (Section 10): approval limits and a change control board.

- Configuration (Section 11): each approved change is saved as a tagged version in GitHub.

- Communication (Section 12): all 13 stakeholder groups are reached on a fixed schedule.

- Quality (Section 13): 12 measures, each with a target, a method and an owner.

The next step is the sponsor's approval of the charter (M1), which starts the project.