IAM SYSTEM DEPLOYMENT — PROJECT PLAN v1.0

Sections 2 and 13, and the References

Fardin Rahman Tanvir · Quality Assurance Lead

Your sections only, taken from the full plan (plan/IAM_ProjectPlan_v1.0.docx). Table, figure and reference numbers match the full plan, so some numbers are skipped. If you change anything here, send the change to Toufiq so it goes into the full plan before release.

# 2. Background research

Section owner: Fardin Rahman Tanvir

## 2.1 Why identity, and why now

Attackers' entry points are shifting. Worldwide, exploited software flaws (31%) now outrank stolen-credential use (13%) as the first step in a breach. In the Asia-Pacific region, though, credential abuse is still 25%, and credentials were taken in 25% of healthcare breaches [1]. Australian data agree: in July–December 2024, phishing, stolen credentials and brute-force attacks caused 151 of 247 cyber incidents reported to the regulator, and health was the worst-hit sector [3]. So identity is a major exposure for an Australian health provider, but not the only one. For this plan: IAM is necessary but not enough on its own. Patching stays with CHG's separate Essential Eight program, and risk R09 covers attacks during the transition.

## 2.2 How strong MFA needs to be

The sources agree that any MFA is far better than none. In Microsoft's own account data, MFA cut the risk of account takeover by 99.22% [4]. They disagree on whether any MFA is enough:

- CISA calls SMS and voice codes a last resort and phishing-resistant MFA the gold standard [5].

- NIST restricts SMS and requires a phishing-resistant option [6].

- Australia's Essential Eight requires phishing-resistant MFA at Maturity Level Two [7].

The 99.22% figure comes from a vendor's own data and was not peer-reviewed; the stricter advice comes from government agencies. Healthcare staff are easy to phish: 14.2% of nearly three million test phishing emails at US health institutions were clicked [8], so a code sent to a phone can be stolen. For this plan: phishing-resistant MFA for all users. Staff on their own devices use passkeys; shared workstations use security keys. SMS is allowed only as an approved exception. Administrators and HR staff are enrolled first.

## 2.3 Usability and the access model in clinical settings

Controls that slow clinicians down lead to workarounds. When two universities made two-factor sign-in compulsory, more than one attempt in twenty failed or was abandoned, and having many separate log-ins made it worse [9]. A review of access control in electronic health records found that rules based on user attributes (such as site or shift) were most common. It also found repeated gaps in MFA, emergency access and audit trails [10]. NIST likewise bases access decisions on identity plus attributes, and advises moving one business process at a time, with new rules run in report-only mode first [11]. No source requires quarterly access reviews; the Essential Eight only asks for administrator access to be rechecked every 12 months [7]. For this plan:

- single sign-on, so staff sign in less often;

- tap-and-go security keys on ward computers;

- roles based on HR job codes, with site and shift rules added;

- emergency (break-glass) accounts that are monitored;

- new rules tested in report-only mode before they are enforced;

- rollout in waves;

- quarterly reviews, chosen because of the risk rather than because a rule requires them.

## 2.4 Project-management practice

The PMBOK Guide (8th edition) organises project work into seven areas — governance, scope, schedule, finance, stakeholders, resources and risk — and expects each project to adapt its methods [12]. ISO 21502 also works with any delivery approach [13]; neither standard picks one. ISO 31000 gives a general risk process [14], but research shows risk management only adds value if the people involved see and use it [15]. For this plan: a hybrid approach. Approval gates, fixed baselines and a change control board handle the contract and compliance work; the SSO waves and pilot are delivered in repeating cycles. Clinical and IT staff join the risk reviews, and every risk has a named owner and a trigger.

# 13. Quality management approach

Section owner: Fardin Rahman Tanvir

Standards. Project quality management follows the principles of ISO 9001:2026 [16]. The IAM system is designed to support CHG's information security management system under ISO/IEC 27001:2022 [17], in particular its controls for access control, identity management, authentication information, access rights, privileged access and secure authentication. Authentication follows NIST SP 800-63B-4 [6], and the target is Essential Eight Maturity Level Two [7].

Table 25 separates quality assurance (is the process right?) from quality control (is the product right?). Table 26 sets measurable targets.

Table 25. Quality assurance and quality control activities

| Quality assurance (process) | Quality control (product) |
| --- | --- |
| - Every deliverable is peer-reviewed through a GitHub pull request before merging - Gate reviews at M2, M4 and M5 check entry and exit criteria - The QA Lead audits the risk register and change log at the midpoint of the build - The partner's configuration is reviewed against the approved design before testing | - System test cases are traced to every requirement - UAT uses real clinical scenarios - Independent penetration test, retested after fixes - Reconciliation reports confirm MFA enrolment and joiner-mover-leaver results - Acceptance criteria (Section 4) checked before sign-off |

Table 26. Quality metrics

| Metric | Target | Method | When | Owner |
| --- | --- | --- | --- | --- |
| Requirements covered by test cases | 100% | Traceability matrix | Before system testing | Fardin |
| System and UAT test cases passed | ≥ 95%; no open severity 1–2 defects | Test log | Gate 3 | Fardin |
| Penetration-test findings | No open high or critical findings | Test report and retest | Before M5 | IAM Architect |
| SSO sign-in success rate | ≥ 99.5% | Platform sign-in logs | Daily in rollout; then weekly | IT Ops |
| Phishing-resistant MFA enrolment | 100% of in-scope identities | Enrolment report | Weekly in rollout | Mahir |
| Leaver access removal | ≤ 4 hours | Monthly sample of 30 HR terminations against application logs | Monthly from go-live | Fardin |
| New starters with access on day one | ≥ 95% | Joiner report and onboarding survey | Monthly | Kritika |
| Orphaned accounts in in-scope apps | 0 | Account reconciliation | End of hypercare; then quarterly | IAM Architect |
| Privileged accounts | ≤ 12, all with FIDO2 keys | PAM report | Go-live; then quarterly | IAM Architect |
| Deliverables peer-reviewed before merge | 100% | GitHub pull request history | Each gate | Mahir |
| Password-reset tickets | 50% fewer than Q1 2027 | Service desk reports | 3 months after go-live | IT Ops |
| Staff satisfaction with sign-in | ≥ 4 out of 5 | Pulse survey | 4 weeks after each site goes live | Kritika |

# References

Section owner: Fardin Rahman Tanvir

[1]	Verizon Business, “2026 Data Breach Investigations Report: Executive summary,” Verizon, Rep. OGES2110526, May 2026. Accessed: Oct. 24, 2026. [Online]. Available: https://www.verizon.com/business/resources/executivebriefs/2026-dbir-executive-summary.pdf

[2]	Office of the Australian Information Commissioner, “Data breach notifications increase to all-time high in 2025, new NDB stats show,” Media release, Jul. 6, 2026. Accessed: Oct. 24, 2026. [Online]. Available: https://www.oaic.gov.au/news/media-centre/data-breach-notifications-increase-to-all-time-high-in-2025,-new-ndb-stats-show

[3]	Office of the Australian Information Commissioner, “Notifiable Data Breaches Report: July to December 2024,” May 13, 2025. Accessed: Oct. 24, 2026. [Online]. Available: https://www.oaic.gov.au/privacy/notifiable-data-breaches/notifiable-data-breaches-publications/notifiable-data-breaches-report-july-to-december-2024

[4]	L. A. Meyer, S. Romero, G. Bertoli, T. Burt, A. Weinert, and J. Lavista Ferres, “How effective is multifactor authentication at deterring cyberattacks?,” arXiv:2305.00945, May 2023, doi: 10.48550/arXiv.2305.00945.

[5]	Cybersecurity and Infrastructure Security Agency, “Implementing phishing-resistant MFA,” Fact sheet, Oct. 2022. Accessed: Oct. 24, 2026. [Online]. Available: https://www.cisa.gov/sites/default/files/publications/fact-sheet-implementing-phishing-resistant-mfa-508c.pdf

[6]	D. Temoshok et al., “Digital identity guidelines: Authentication and authenticator management,” National Institute of Standards and Technology, Gaithersburg, MD, USA, NIST SP 800-63B-4, Jul. 2025, doi: 10.6028/NIST.SP.800-63b-4.

[7]	Australian Signals Directorate, “Essential Eight maturity model,” Australian Cyber Security Centre, Nov. 27, 2023. Accessed: Oct. 24, 2026. [Online]. Available: https://www.cyber.gov.au/publication/essential-eight-maturity-model

[8]	W. J. Gordon et al., “Assessment of employee susceptibility to phishing attacks at US health care institutions,” JAMA Netw. Open, vol. 2, no. 3, Mar. 2019, Art. no. e190393, doi: 10.1001/jamanetworkopen.2019.0393.

[9]	J. Reynolds et al., “Empirical measurement of systemic 2FA usability,” in Proc. 29th USENIX Secur. Symp., Aug. 2020, pp. 127–143.

[10]	U. N. Cobrado, S. Sharief, N. G. Regahal, E. Zepka, M. Mamauag, and L. C. Velasco, “Access control solutions in electronic health record systems: A systematic review,” Inform. Med. Unlocked, vol. 49, 2024, Art. no. 101552, doi: 10.1016/j.imu.2024.101552.

[11]	S. Rose, O. Borchert, S. Mitchell, and S. Connelly, “Zero trust architecture,” National Institute of Standards and Technology, Gaithersburg, MD, USA, NIST SP 800-207, Aug. 2020, doi: 10.6028/NIST.SP.800-207.

[12]	Project Management Institute, A Guide to the Project Management Body of Knowledge (PMBOK Guide), 8th ed. Newtown Square, PA, USA: PMI, 2025.

[13]	Project, Programme and Portfolio Management — Guidance on Project Management, ISO 21502:2020, International Organization for Standardization, Geneva, Switzerland, Dec. 2020.

[14]	Risk Management — Guidelines, ISO 31000:2018, International Organization for Standardization, Geneva, Switzerland, Feb. 2018.

[15]	P. Willumsen, J. Oehmen, V. Stingl, and J. Geraldi, “Value creation through project risk management,” Int. J. Proj. Manag., vol. 37, no. 5, pp. 731–749, Jul. 2019, doi: 10.1016/j.ijproman.2019.01.007.

[16]	Quality Management Systems — Requirements, ISO 9001:2026, International Organization for Standardization, Geneva, Switzerland, Sep. 2026.

[17]	Information Security, Cybersecurity and Privacy Protection — Information Security Management Systems — Requirements, ISO/IEC 27001:2022, International Organization for Standardization, Geneva, Switzerland, Oct. 2022.