IAM SYSTEM DEPLOYMENT — PROJECT PLAN v1.0

Sections 10 and 11, and Appendices A–C

Ahmed Mahir Daiyan · Change and Configuration Manager

Your sections only, taken from the full plan (plan/IAM_ProjectPlan_v1.0.docx). Table, figure and reference numbers match the full plan, so some numbers are skipped. If you change anything here, send the change to Toufiq so it goes into the full plan before release.

# 10. Change request and change management process

Section owner: Ahmed Mahir Daiyan

Change control protects the scope, schedule and cost baselines approved at Gate 1. Figure 3 shows the process.

- Raise: anyone can submit a change request (CR) on the form in Table 19.

- Log: within one working day the Change and Configuration Manager logs it as CR-###.

- Assess: within five days the project manager, IAM Architect and QA Lead assess its impact on scope, time, cost, quality and risk.

- Decide: the board in Table 20 decides, within the approval limits in the figure.

- Implement: approved changes are made on a GitHub branch (cr-###), merged after the QA Lead reviews them, and saved as a new tagged baseline.

- Close: every decision is recorded in the change log (Table 21).

Figure 3. Change control process and approval authority

Table 19. Change request form template

| CR ID and date raised | CR-### (assigned by Change and Configuration Manager); dd/mm/yyyy |
| --- | --- |
| Requested by | Name, role, department |
| Description of change |  |
| Reason and benefit |  |
| WBS elements affected | e.g. 1.4.3, M5 |
| Impact: scope | Deliverables added, removed or changed |
| Impact: schedule | Working days; milestones moved; effect on critical path |
| Impact: cost | AUD; funding source (contingency, management reserve, new funds) |
| Impact: quality and risk | Effect on acceptance criteria; new or changed risks (IDs) |
| Urgency | Normal / urgent / emergency |
| Recommendation | Project manager's recommendation and options considered |
| Decision | Approved / rejected / deferred, with reason; approver name and date |
| Implementation | Owner; GitHub branch and baseline tag; Jira card |

Table 20. Change control board (meets fortnightly, or within two working days for an urgent CR)

| CCB role | Member | Part in decisions |
| --- | --- | --- |
| Chair | Catherine Doyle, Chief Operating Officer (sponsor) | Final approval; casting vote |
| Members | Project manager (presents CRs); IAM Architect; IT Operations Manager; QA Lead; Director of Nursing's delegate (clinical impact) | Vote |
| Secretary | Change and Configuration Manager (Mahir) | Keeps the change log; no vote |

Table 21. Change log (the two rows are examples of how to fill it in)

| ID | Date | Change | Impact | Decision | Approver | Baseline | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CR-001 | 18 Feb 2027 | Add the dental practice system to phase 1 SSO | +8 days on wave 3; +AUD 22,000 | Deferred to phase 2 | CCB | – | Closed |
| CR-002 | 1 Mar 2027 | Extra night-shift training sessions at the day hospital | 0 days (1.6.1 has float); +AUD 3,500 from contingency | Approved | Project manager | baseline-1.1 | Closed |

# 11. Configuration management (GitHub)

Section owner: Ahmed Mahir Daiyan

Every project artefact that defines a baseline is a configuration item and is kept under version control in one GitHub repository:

https://github.com/AR13X3/iam-deployment-project-plan

Table 22. Repository structure

| Folder or file | Contents | Owner |
| --- | --- | --- |
| README.md | Purpose, folder guide, branch and commit rules, how to raise a CR | Mahir |
| plan/ | Plan drafts and released versions (.docx) | Toufiq |
| schedule/ | GanttProject source (IAM_Schedule.gan), schedule.csv, Gantt image | Toufiq |
| wbs/ | WBS outline (wbs.csv) and diagram | Toufiq |
| risk/ | Risk register (risk_register.csv) | Toufiq |
| change-management/ | Change log, CR form and process flowchart | Mahir |
| templates/ | Issue log, status report and CR templates | Kritika |
| config/ (from build) | Exported IAM platform configuration (access policies, role definitions, provisioning mappings) as JSON | IAM Architect |

Table 23. Version-control rules

| Practice | Rule |
| --- | --- |
| Branches | main is protected. Each owner works on a branch for their area (charter, schedule, risk, change-management, quality, communication) and merges through a pull request approved by another member. Approved change requests use cr-### branches |
| Commits | One commit per meaningful change, with an imperative message naming the area, e.g. risk: add EMV for high risks or schedule: add SS+5d link for 1.4.4 |
| Versions | Drafts are tagged v0.x; the released plan is GitHub Release v1.0; later approved baselines are tagged baseline-1.x |
| Readable history | Risk register, schedule, WBS and logs are kept as CSV alongside the .docx so changes show line by line |
| Status accounting and audit | At each gate the QA Lead checks that the tagged baseline matches the approved documents and the change log |

During the build, platform configuration (MFA and conditional access policies, role definitions, provisioning mappings) is exported to config/, so every production change can be traced to an approved CR. Figure 4, Figure 5 and Figure 6 show the repository.

INSERT SCREENSHOT README of the repository (github.com/AR13X3/iam-deployment-project-plan)

Figure 4. Repository README

INSERT SCREENSHOT Commit history showing commits from all four members on at least three different days (Insights → Contributors also works)

Figure 5. Commit history

INSERT SCREENSHOT A merged pull request with another member's approval

Figure 6. Merged pull request with review

# Appendix A. Jira project evidence

Section owner: Ahmed Mahir Daiyan

The Jira Scrum project holds one epic for the plan and one card per section, each assigned to its owner with a due date. The screenshots below show the board during the sprint, the backlog, a card's comments and history, and the timeline.

INSERT SCREENSHOT Jira board mid-sprint, with cards for all four members in To Do, In Progress and Done

Figure 7. Jira board during the sprint

INSERT SCREENSHOT Jira backlog with the plan epic and one issue per section

Figure 8. Jira backlog

INSERT SCREENSHOT One Jira card showing comments from another member and its history

Figure 9. Card comments and history

INSERT SCREENSHOT Jira timeline view

Figure 10. Jira timeline

# Appendix B. GitHub history

Section owner: Ahmed Mahir Daiyan

INSERT SCREENSHOT Insights → Contributors graph, and the list of merged pull requests (Pull requests → Closed)

Figure 11. Contributors and merged pull requests

# Appendix C. Working calendar

Section owner: Ahmed Mahir Daiyan

The schedule uses a Monday-to-Friday calendar with these non-working days. All other weekdays are working days.

Table 27. Non-working weekdays in the schedule

| Date | Reason |
| --- | --- |
| 24 Dec 2026 | Christmas shutdown |
| 25 Dec 2026 | Christmas Day |
| 28 Dec 2026 | Boxing Day (additional day) |
| 29 Dec 2026 | Christmas shutdown |
| 30 Dec 2026 | Christmas shutdown |
| 31 Dec 2026 | Christmas shutdown |
| 1 Jan 2027 | New Year's Day |
| 26 Jan 2027 | Australia Day |
| 26 Mar 2027 | Good Friday |
| 29 Mar 2027 | Easter Monday |
| 14 Jun 2027 | King's Birthday |